## Management Products
PROJECT SIGN-OFF GUIDELINE Documents produced and owned by the Project. Original signed-off versions to reside in Project Files
Type of Signatory | Operational |  |  | Project Specific |  |  |  | Specialist Expertise (eg Marketing / Finance/ Communications) |  |  |  | Group Functions |  |  | Other eg External Parties
Role | Business Process Owner | Business Unit Manager | Business Owner | Project Process Analyst | Project Manager | Sponsor (Usually Executive) | Steering Committee Members | Project Resource | Manager | Compliance | Risk | Group Legal | Group Risk | Other
Business Proposal |  |  | If known - Confirms acceptance of proposal and takes accountability as Business Owner for subsequent implementation |  |  | Confirms GSE approval of the proposal. Takes accountability as Sponsor for the subsequent implementation |  |  | Confirms accuracy and acceptance of contents | Required if the Proposal is created in response to a Compliance issue : Signature indicates that the proposal adequately addresses the issue | Required if the Proposal is created in response to a business risk : Signature indicates that the proposal adequately addresses the risk | Required if the Proposal has Legal implications for the organisation as a whole. Signature indicates acknowedgement and approval of the Proposal | Required if the Proposal has Risk implications for the organisation as a whole. Signature indicates acknowedgement and approval of the Proposal |  | If External Parties are Key Stakeholders to the Proposal in an active role-playing sense. Signature indicates confirmation of accuracy and acceptance
Business Process Proposal | Content Accuracy & Acceptance of contents | Content Accuracy & Acceptance of contents | Acceptance - Satisfied that all necessary unit parties have approved. | Correctness of content ito meeting project requirement and ensuring end-to-end business process integrity | Confirms that the BPP aligns with the Proposal as accepted above and awareness of associated business decisions | Confirms that the BPP aligns with the Proposal as accepted above and acceptance of associated business decisions | Confirms that the BPP aligns with the Proposal as accepted above and acceptance of associated business decisions |  | Confirms accuracy and acceptance of contents | Compliance are aware of and have ensured the consideration of compliance concerns presented to the Business by the implementation of the proposed solution | Risk Management are aware of and accept responsibility for tracking and driving the management of all Risks presented to the Business by the implementation of the proposed solution | Conditional Requirement - If Corporate processes affected : Corporate Legal acceptance of the proposed business processes | Conditional Requirement - If Corporate processes affected : Corporate Risk acceptance of the proposed business processes
Scope of Work |  | Content Accuracy & Acceptance of contents | Acceptance - Satisfied that all necessary unit parties have approved. | Where required - (eg. If Business Process Design is signed off as part of Business Proposal this signature would be extraneous. ) | PM acceptance of responsibility to deliver the scope as defined | Sponsor acceptance of scope as defined | Steercom Member/s acceptance of scope as defined |  | Expert's acceptance of scope as defined | Compliance acceptance of scope as defined | Risk Management are aware of and accept responsibility for tracking and driving the management of all Risks presented to the Business by the implementation of the scope as defined | Conditional requirement | Conditional requirement
Benefits Statement |  | Content Accuracy & Acceptance of contents | Acceptance - Satisfied that all necessary unit parties have approved. |  | PM acknowledgement of the expected associated benefits and the associated measurement requirements | Sponsor acceptance of benefits as defined | Steercom Member/s acceptance of benefits as defined |  | Expert's acceptance of benefits as defined | Required if the project in response to a Compliance issue : Signature indicates that the benefits as defined address the issue | Required if the project in response to a Business Risk : Signature indicates that the benefits as defined address the risk | Required if there are Risk implications for the organisation as a whole. Signature indicates acknowedgement and approval of the benefits | Required if there are Legal implications for the organisation as a whole. Signature indicates acknowedgement and approval of the benefits |  | Conditional Requirement - If External Parties are Key Stakeholders to the Proposal in an active role-playing sense. Signature indicates confirmation of accuracy and acceptance of benegits as stated
Initial Delivery Plan & Resourcing Agreement/s | Acceptance of plan ito resource allocation and delivery schedule | Acceptance of plan ito resource allocation and delivery schedule | Acceptance of plan ito resource allocation and delivery schedule | Conditional - Acceptance of plan ito resource allocation and delivery schedule | PM acceptance of responsibility to deliver against the plan as defined | Acceptance of plan ito resource allocation and delivery schedule | Acceptance of plan ito resource allocation and delivery schedule | Conditional requirement - Acceptance of plan ito resource allocation and delivery schedule | Acceptance of plan ito resource allocation and delivery schedule |  |  | Conditional requirement - Acceptance of plan ito resource allocation and delivery schedule | Conditional requirement - Acceptance of plan ito resource allocation and delivery schedule |  | Conditional requirement - Acceptance of plan ito resource allocation and delivery schedule
Budget |  |  | Budget presents accurate view of associated costs. Acceptance of budget management plan |  | PM acceptance of responsibility to control and manage expenditure against budget as stated | Budget presents accurate view of associated costs. Acceptance of budget management plan | Budget presents accurate view of associated costs. Acceptance of budget management plan
Functional Specification
Note on E3: May be the BU Manager if this person has been designated as the ultimate Business Owner for the project outcome
Note on A5: This document gives a high level description of the opportunity, recommendation and business impact/s, including high-level benefits and costs
Note on A6: This document provides a process view of how the solution is to be implemented….including details of all business decisions required to enable the process/es
Note on A8: Provides a detailed breakdown of what the project WILL and WILL NOT deliver against the stated objectives, as well as critical success factors, assumptions and constraints. Once signed off any change to scope requires a Change Request(Which would in turn require sign-off)
Note on A9: All the benefits as identified in the Business Proposal. State which need to be measured through the duration of the project. Provides high level view of any existing business processes that will be affected / new processes that will be required to enable benefit tracking
Note on A10: Detailed MS-Project delivery plan (in accessible format to full audience) Developed from Scope. Iteratively amended until acceptable to Sponsor and Steercom with amendments to scope being made accordingly.
Note on A11: Budgetary requirements for the project (May need to cater for tracking of operational budget being directed towards the project as well as capital expenditure) Agreement as to how budget is to be managed (Who needs to approve various levels of spend etc)