## Template
Schedule Validation Template
| Status | Action | Owner | Due | Notes
Deliverables | Are the most important items (key services deliverables) shown at the highest level of WBS? |  |  |  | If you do all of the detail tasks, will you have completely accomplished the summary deliverable?
Has the WBS been shared with the Customer/partner/service provider for identification of key services deliverables?
Is there any duplication of deliverables in the WBS?
Is it clear how deliverables will be created and what the activities involved are?
Scope and breakdown | Does the WBS represent the entire scope of the project?
| Does the overall level of detail appear reasonable for the type of project? |  |  |  | Is the WBS set at appropriate level for size and type of project?
| Are customer/client tasks included in the WBS? |  |  |  | Customer tasks should align with Customer Responsibilities in the Statement of Work.
Milestones | Are there enough milestones identified? (Roughly, one milestone for each deliverable)
Are there revalidation checkpoints when moving from one phase to next (for multi-phase projects)?
Governance | Are governance tasks separated out into their own section?
Is there sufficient project management time across entire project?
Is there sufficient architectural leadership across the entire project?
Structure | Does the WBS map to a methodology & does it make sense within that context?
Estimates | Did the person who is most familiar with the task estimate the task itself? |  |  |  | Check the accuracy of the task after the work had been performed.
More often than not, estimators are optimistic by nature. PM should take this tendency into account by adding a sufficient time into the estimate buffer
Risk | Did you document any risks for the tasks?
Dependencies | Are the task dependencies implemented with the correct logic? |  |  |  | Steps to determine the selection of logic between tasks: 1. What do you need to do this task? 2. Does the start or finish of the predecessor drive the successor? 3. Does the predecessor drive the start or the finish of the successor? 4. Should there be a gap or overlap between the two tasks? 5. Is the gap/overlap absolute or does it depend on duration of the predecessor? 6. How much lead or lag should be applied among the tasks?
Does the overall sequence of phases/deliverables make sense?
Is the network of logic complete (i.e. no loose ends, project end milestone)
Are the resource dependencies accounted for?
Resources | Have all the resources been identified in the resource sheet?
Are all resources named completely and consistently using a naming convention?
Is there any duplication of resources?
| Is the workload of resources reasonable? |  |  |  | Resources may be overallocated.
Tasks, assignments, durations | Has the correct task type been selected? |  |  |  | In most situations, the estimate is formulated in duration units or work units. Tip: Provide estimates in duration units for tasks that are not discretely divisible into work for individuals (e.g., meetings). Provide estimates in work units when the number of people assigned will proportionally reduce/increase the duration of the task.
Are there any assignments on summary tasks?
Does each detail task have at least one human resource assigned?
Are durations >=1day; <=10d
Review | Has the WBS been vetted by an independent party or a senior architect (not part of WBS creation team) for technical soundness & completeness?